## Chronology
Selected Hubstaff Gap Implementation Roadmap
Prepared 2026-06-13. Scope excludes screenshots and broad Hubstaff clone features.
Seq | Phase | Feature | Branches | Depends on | Backend implementation | Frontend implementation | Acceptance summary
1 | Foundation | Manual start/stop timer | 2 | Auth, clients, matters, workSessions, activities, timeEntries | Harden WorkSession start/current/pause/resume/stop/discard APIs, add explicit idempotency/error contracts, ensure stop always creates Activity + submitted TimeEntry by default. | Connect client, matter, task/work type, work tool, timer controls, save draft, save+submit, retry-on-save-failure, and current-session restore. | User can select client/matter/task/work type/tool, start one active meter, pause/resume, stop, and see a submitted work entry. Refreshing the page restores active session. Duplicate active meters are blocked.
2 | Foundation | Client, matter, payment, and task tracking | 3 | Manual timer, tasks, clients, matters, invoices, payments | Add/verify taskId on WorkSession/Activity/TimeEntry/Billable where appropriate; expose matter payment context and unpaid invoice/payment summaries for timer context. | Add task selector, matter/client auto-fill, recent payment/balance context, and task-to-meter start actions from task pages. | Every tracked work entry can be traced to client + matter and optionally task. User can start meter from task or meter page. Matter payment context is visible without blocking tracking.
3 | Approval pipeline | Payroll, timesheet, and work entry approval | 4 | Manual timer, task tracking, rates, users/roles | Create timesheet period model/API, submitted time queue, approve/reject transitions, immutable approval audit, payroll period/run models, and payable approved time aggregation. | Build manager time approval queue, weekly timesheet view, rejection correction flow, payroll run preview, and payroll approval screens. | Worker submits entries; manager/admin approves or rejects with reason; approved entries lock for billing/payroll; payroll preview aggregates approved payable time by user and period.
4 | Monitoring core | Activity tracking: keyboard/mouse activity | 3 | Manual timer, desktop/mobile agent contract | Add activity sample schema for keyboard/mouse counts, active/inactive seconds, sampling window, device/app source, aggregation by work session, privacy-safe no-keystroke policy. | Web/desktop agent contract sends periodic activity samples; UI shows activity percentage by session/day without exposing keystrokes or sensitive content. | For each active session, system stores time-bucketed keyboard/mouse counts and computes activity %. No actual key values or content are stored. Managers can view aggregate activity by session.
5 | Monitoring core | Desktop/mobile app and URL tracking | 4 | Manual timer, activity signal ingestion | Create app/url usage event model with sessionId, appName, url/domain, title optional, startedAt/endedAt/duration, platform, and privacy filters. | Desktop/mobile agent sends active app and URL only; web UI shows app/URL timeline and totals by session/user/day. | Tracked session records app name and URL/domain duration only. No screenshots or page content are captured. Reports show app/URL time totals and session timeline.
6 | Monitoring core | Idle time detection | 2 | Manual timer, keyboard/mouse activity, app/url events | Use activity samples and heartbeat gaps to detect idle periods, store idle intervals, support discard/keep decisions, and recalculate payable/session duration. | Prompt user to keep or discard idle time when returning; show idle markers in session review and approval queue. | If user is inactive beyond threshold, idle interval is detected. User/admin can classify idle time. Approved payable duration excludes discarded idle time.
7 | Workforce ops | Attendance and leave approval | 4 | Users, work sessions, payroll periods | Create attendance day records from first/last activity, expected schedules, lateness/absence flags, leave request model, approval workflow, holiday calendar. | Attendance dashboard, employee attendance calendar, leave request form, manager leave approval queue, and absence exceptions. | System can show present/absent/late/leave status per employee/day. Employees request leave; managers approve/reject; approved leave affects attendance and payroll preview.
8 | Analytics | Workforce analytics | 3 | All prior tracking, approval, attendance, and payroll data | Add aggregates for tracked hours, billable %, activity %, idle %, app/URL usage, approval SLA, attendance, utilization, and payroll-ready totals. | Build dashboards for managers/admins with filters by user/team/client/matter/date and exportable reports. | Admin can answer: who worked, on what client/matter/task, for how long, activity %, idle time, approval status, attendance, and payroll/billable readiness.

## Branch Plan
Git Branch Plan
Recommended branch sequencing. Branch names use the repository convention codex/<scope>.
Feature seq | Feature | Branch seq | Branch name | Primary area | Start condition | Branch acceptance focus
1 | Manual start/stop timer | 1 | codex/work-meter-backend-contract | Backend | Start after prior feature acceptance passes | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
1 | Manual start/stop timer | 2 | codex/work-meter-frontend-flow | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
2 | Client, matter, payment, and task tracking | 1 | codex/tracking-context-backend | Backend | Start after prior feature acceptance passes | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
2 | Client, matter, payment, and task tracking | 2 | codex/task-meter-linkage | Full stack | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
2 | Client, matter, payment, and task tracking | 3 | codex/payment-context-ui | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
3 | Payroll, timesheet, and work entry approval | 1 | codex/timesheet-backend | Backend | Start after prior feature acceptance passes | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
3 | Payroll, timesheet, and work entry approval | 2 | codex/time-entry-approval-ui | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
3 | Payroll, timesheet, and work entry approval | 3 | codex/payroll-foundation | Backend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
3 | Payroll, timesheet, and work entry approval | 4 | codex/payroll-approval-ui | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
4 | Activity tracking: keyboard/mouse activity | 1 | codex/activity-signal-ingestion | Backend | Start after prior feature acceptance passes | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
4 | Activity tracking: keyboard/mouse activity | 2 | codex/activity-agent-contract | Backend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
4 | Activity tracking: keyboard/mouse activity | 3 | codex/activity-review-ui | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
5 | Desktop/mobile app and URL tracking | 1 | codex/app-url-event-schema | Backend | Start after prior feature acceptance passes | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
5 | Desktop/mobile app and URL tracking | 2 | codex/desktop-agent-mvp | Backend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
5 | Desktop/mobile app and URL tracking | 3 | codex/mobile-agent-mvp | Backend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
5 | Desktop/mobile app and URL tracking | 4 | codex/app-url-timeline-ui | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
6 | Idle time detection | 1 | codex/idle-detection-backend | Backend | Start after prior feature acceptance passes | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
6 | Idle time detection | 2 | codex/idle-resolution-ui | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
7 | Attendance and leave approval | 1 | codex/attendance-backend | Backend | Start after prior feature acceptance passes | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
7 | Attendance and leave approval | 2 | codex/leave-backend | Backend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
7 | Attendance and leave approval | 3 | codex/attendance-ui | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
7 | Attendance and leave approval | 4 | codex/leave-approval-ui | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
8 | Workforce analytics | 1 | codex/workforce-analytics-backend | Backend | Start after prior feature acceptance passes | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
8 | Workforce analytics | 2 | codex/productivity-dashboard | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.
8 | Workforce analytics | 3 | codex/exportable-workforce-reports | Frontend | Start after previous branch in same feature | Keep scope narrow; add route/model tests for backend and UI/API integration checks for frontend.

## Acceptance Criteria
Acceptance Criteria By Feature And Layer
Backend and frontend criteria are separated so QA can verify both independently.
Seq | Feature | Layer | Implementation requirement | Acceptance criteria
1 | Manual start/stop timer | Backend | Harden WorkSession start/current/pause/resume/stop/discard APIs, add explicit idempotency/error contracts, ensure stop always creates Activity + submitted TimeEntry by default. | User can select client/matter/task/work type/tool, start one active meter, pause/resume, stop, and see a submitted work entry. Refreshing the page restores active session. Duplicate active meters are blocked.
1 | Manual start/stop timer | Frontend | Connect client, matter, task/work type, work tool, timer controls, save draft, save+submit, retry-on-save-failure, and current-session restore. | User can select client/matter/task/work type/tool, start one active meter, pause/resume, stop, and see a submitted work entry. Refreshing the page restores active session. Duplicate active meters are blocked.
2 | Client, matter, payment, and task tracking | Backend | Add/verify taskId on WorkSession/Activity/TimeEntry/Billable where appropriate; expose matter payment context and unpaid invoice/payment summaries for timer context. | Every tracked work entry can be traced to client + matter and optionally task. User can start meter from task or meter page. Matter payment context is visible without blocking tracking.
2 | Client, matter, payment, and task tracking | Frontend | Add task selector, matter/client auto-fill, recent payment/balance context, and task-to-meter start actions from task pages. | Every tracked work entry can be traced to client + matter and optionally task. User can start meter from task or meter page. Matter payment context is visible without blocking tracking.
3 | Payroll, timesheet, and work entry approval | Backend | Create timesheet period model/API, submitted time queue, approve/reject transitions, immutable approval audit, payroll period/run models, and payable approved time aggregation. | Worker submits entries; manager/admin approves or rejects with reason; approved entries lock for billing/payroll; payroll preview aggregates approved payable time by user and period.
3 | Payroll, timesheet, and work entry approval | Frontend | Build manager time approval queue, weekly timesheet view, rejection correction flow, payroll run preview, and payroll approval screens. | Worker submits entries; manager/admin approves or rejects with reason; approved entries lock for billing/payroll; payroll preview aggregates approved payable time by user and period.
4 | Activity tracking: keyboard/mouse activity | Backend | Add activity sample schema for keyboard/mouse counts, active/inactive seconds, sampling window, device/app source, aggregation by work session, privacy-safe no-keystroke policy. | For each active session, system stores time-bucketed keyboard/mouse counts and computes activity %. No actual key values or content are stored. Managers can view aggregate activity by session.
4 | Activity tracking: keyboard/mouse activity | Frontend | Web/desktop agent contract sends periodic activity samples; UI shows activity percentage by session/day without exposing keystrokes or sensitive content. | For each active session, system stores time-bucketed keyboard/mouse counts and computes activity %. No actual key values or content are stored. Managers can view aggregate activity by session.
5 | Desktop/mobile app and URL tracking | Backend | Create app/url usage event model with sessionId, appName, url/domain, title optional, startedAt/endedAt/duration, platform, and privacy filters. | Tracked session records app name and URL/domain duration only. No screenshots or page content are captured. Reports show app/URL time totals and session timeline.
5 | Desktop/mobile app and URL tracking | Frontend | Desktop/mobile agent sends active app and URL only; web UI shows app/URL timeline and totals by session/user/day. | Tracked session records app name and URL/domain duration only. No screenshots or page content are captured. Reports show app/URL time totals and session timeline.
6 | Idle time detection | Backend | Use activity samples and heartbeat gaps to detect idle periods, store idle intervals, support discard/keep decisions, and recalculate payable/session duration. | If user is inactive beyond threshold, idle interval is detected. User/admin can classify idle time. Approved payable duration excludes discarded idle time.
6 | Idle time detection | Frontend | Prompt user to keep or discard idle time when returning; show idle markers in session review and approval queue. | If user is inactive beyond threshold, idle interval is detected. User/admin can classify idle time. Approved payable duration excludes discarded idle time.
7 | Attendance and leave approval | Backend | Create attendance day records from first/last activity, expected schedules, lateness/absence flags, leave request model, approval workflow, holiday calendar. | System can show present/absent/late/leave status per employee/day. Employees request leave; managers approve/reject; approved leave affects attendance and payroll preview.
7 | Attendance and leave approval | Frontend | Attendance dashboard, employee attendance calendar, leave request form, manager leave approval queue, and absence exceptions. | System can show present/absent/late/leave status per employee/day. Employees request leave; managers approve/reject; approved leave affects attendance and payroll preview.
8 | Workforce analytics | Backend | Add aggregates for tracked hours, billable %, activity %, idle %, app/URL usage, approval SLA, attendance, utilization, and payroll-ready totals. | Admin can answer: who worked, on what client/matter/task, for how long, activity %, idle time, approval status, attendance, and payroll/billable readiness.
8 | Workforce analytics | Frontend | Build dashboards for managers/admins with filters by user/team/client/matter/date and exportable reports. | Admin can answer: who worked, on what client/matter/task, for how long, activity %, idle time, approval status, attendance, and payroll/billable readiness.

## Milestones
Suggested Delivery Milestones
Chronology grouped into implementation milestones and release gates.
Milestone | Name | Feature scope | Branch count | Build scope | Exit criteria | Release recommendation
M1 | Meter MVP hardening | Features 1-2 | 5 branches | Timer, context tracking, task/client/matter/payment context | Meter can submit traceable work entries | Release to internal legal users
M2 | Approval and payroll base | Feature 3 | 4 branches | Timesheets, work entry approval, payroll foundation | Approved work is locked and payroll-ready | Release to admins/managers
M3 | Monitoring core | Features 4-6 | 9 branches | Keyboard/mouse activity, app/URL tracking, idle detection | Privacy-safe monitoring data available per session | Pilot with opt-in team
M4 | Workforce ops | Feature 7 | 4 branches | Attendance and leave approval | Attendance/leave affects payroll preview | Release to HR/admin
M5 | Analytics | Feature 8 | 3 branches | Workforce analytics and exports | Managers can view productivity/utilization/approval/attendance reports | Executive dashboard release

## Risks Decisions
PM Risks And Product Decisions
Decisions to make before implementation starts.
Decision area | Risk | Why it matters | Recommended decision | Needed by
Privacy policy | High | Keyboard/mouse and app/URL tracking can feel like surveillance. | Define no-keystroke/no-screenshot policy, consent copy, role visibility, retention. | Before Feature 4
Agent strategy | High | Desktop/mobile tracking requires local agents, not just web app. | Choose platform order: Windows first, then macOS, then Android/iOS if needed. | Before Feature 5
Task model linkage | Medium | Current meter is matter-oriented; task tracking needs taskId across records. | Confirm whether task is optional or required for every tracked session. | Before Feature 2
Payroll jurisdiction | High | Payroll rules differ by country/state and employment type. | Start with payroll-ready export/preview, not payment automation. | Before Feature 3
Approval ownership | Medium | Partner/admin/self-approval rules need business decision. | Prevent self-approval; define manager/partner/admin hierarchy. | Before Feature 3
Idle-time treatment | Medium | Discarding idle time affects trust and payable time. | Let user classify idle first; allow manager override with audit. | Before Feature 6
Analytics quality | Medium | Analytics are only useful after tracking data is reliable. | Build analytics last and keep definitions formula-backed/exportable. | Before Feature 8