## Executive Summary
Lexora Solo-Lawyer MVP
Product and Scrum delivery tracker ¦ 8 weeks ¦ 4 sprints ¦ 320 hours ¦ Controlled pilot with 3-5 independent lawyers
Delivery KPI | Value | Sprint | Weeks | Planned h | Buffer h | Goal
Core workflow | Client -> Matter -> Task -> Work -> Review -> Billable -> Invoice -> Payment | S1 | Weeks 1-2 | 72 | 8 | Create the secure solo account foundation and reliable client/matter system.
Current estimated completion | 55-60% | S2 | Weeks 3-4 | 72 | 8 | Capture legal work from tasks, timer, manual entry, Gmail and research into one review queue.
Target MVP completion | 100% of frozen focused scope | S3 | Weeks 5-6 | 72 | 8 | Turn reviewed work and expenses into accurate, professional invoices.
Planned delivery | 288 hours | S4 | Weeks 7-8 | 72 | 8 | Send invoices, record payments, report income/outstanding balances and launch the pilot safely.
Protected contingency | 32 hours
Release target | Controlled pilot, not a legal ERP | Sprint | Planned | Buffer
|  | S1 | 72 | 8
Release gate | Required result | S2 | 72 | 8
G1 | Workspace A cannot read or mutate Workspace B data. | S3 | 72 | 8
G2 | Every supported capture produces at most one work entry. | S4 | 72 | 8
G3 | Every work entry and expense can be invoiced at most once.
G4 | Invoice totals, payment allocations and reports reconcile exactly.
G5 | Finalised invoices are locked and corrections are audited.
G6 | Backup restoration, error monitoring and production health checks pass.
G7 | All retained screens have loading, empty, error and recovery states.
G8 | No P0/P1 defect remains open at pilot launch.
North-star promise | Capture every piece of legal work and turn it into a paid invoice with minimal effort.

## Sprint Plan
Eight-Week Sprint Plan
Four two-week sprints; 72 planned hours plus 8 hours contingency per sprint
Sprint | Weeks | Goal | Branches | Planned h | Buffer h | Review demo | Exit criteria | Status
S1 | Weeks 1-2 | Create the secure solo account foundation and reliable client/matter system. | A-D | 72 | 8 | Register a solo account, complete onboarding, create a client and matter, and prove workspace isolation. | Authentication, workspace scoping, client CRUD and matter CRUD pass integration tests. | Not Started
S2 | Weeks 3-4 | Capture legal work from tasks, timer, manual entry, Gmail and research into one review queue. | E-H | 72 | 8 | Start work from a task, stop the timer, recover an offline capture and review one unified work entry. | Every supported capture source creates exactly one workspace-scoped work entry. | Not Started
S3 | Weeks 5-6 | Turn reviewed work and expenses into accurate, professional invoices. | I-L | 72 | 8 | Review time, apply a rate, add an expense, generate and lock a GST invoice PDF. | Ready-to-bill work cannot be billed twice; invoice totals reconcile server-side. | Not Started
S4 | Weeks 7-8 | Send invoices, record payments, report income/outstanding balances and launch the pilot safely. | M-P | 72 | 8 | Send an invoice, record a partial payment, issue a receipt and verify dashboard/report balances. | End-to-end regression, backups, monitoring and pilot onboarding gates pass. | Not Started
Scrum ceremony | Cadence
Sprint planning | First morning of each sprint; freeze goal and branch order
Daily plan | 15 minutes; one shippable vertical slice and its verification command
Daily review | 15 minutes; update status, remaining hours, blocker and evidence
Refinement | Friday, 45 minutes; split work and defend non-goals
Sprint review | Working demo using real APIs and sprint exit criteria
Retrospective | One process improvement applied in the next sprint

## Branch Tracker
Branch / Work-Package Tracker
Sequential child branches from codex/solo-lawyer-mvp; update status and evidence daily
No. | Sprint | Branch | Epic | Goal | Screens / States | Backend / API | Acceptance Criteria | Planned h | SP | Status | Dependency | Commit Message | Verification Evidence
A | S1 | codex/solo-product-shell | Foundation | Introduce solo product mode, focused navigation and shared UX states while hiding enterprise-only modules. | Focused app shell; solo navigation; fallback states; not-found and offline states | PRODUCT_MODE configuration; route exposure map; no schema change | Only focused MVP routes appear; excluded modules cannot be reached through navigation; loading, empty, error and retry states are reusable. | 12 | 6 | Not Started | main | feat(solo): add focused product shell
B | S1 | codex/solo-auth-onboarding | Account | Simplify registration and login to one owner account and capture practice, tax, invoice and payment defaults during onboarding. | Login; register; forgot/reset password; onboarding; owner profile; practice settings | Auth current-user routes; workspace creation; owner profile/settings; session revocation | A lawyer registers without choosing a role, receives one workspace and can complete/edit practice settings. | 20 | 10 | Not Started | codex/solo-product-shell | feat(auth): add solo owner onboarding
C | S1 | codex/workspace-isolation | Security | Enforce workspace ownership across every retained resource and migrate legacy firm records safely. | No new primary screen; access-denied and migration-safe error states | workspaceId/firmId migration; request workspace context; scoped queries; ownership validators | Workspace A cannot read or mutate Workspace B records; ownership fields cannot be supplied by clients. | 20 | 10 | Not Started | codex/solo-auth-onboarding | security: enforce solo workspace isolation
D | S1 | codex/solo-clients-matters | Practice records | Complete client and matter records for a solo practice, including contacts, GST, billing terms, court details and financial summaries. | Client list/form/detail; matter list/form/detail; client balance; matter financial summary | Client contacts/notes; matter numbering; matter billing method; scoped summaries | Client and matter CRUD works with validation, archive/reopen, search and workspace ownership. | 20 | 10 | Not Started | codex/workspace-isolation | feat(practice): complete solo clients and matters
E | S2 | codex/solo-tasks-daily-work | Daily work | Simplify tasks for one lawyer and allow any task to launch a pre-filled work session. | Task list; task form; task detail; My Work Today | Task CRUD; due/priority/checklist; meter context handoff | The owner can create, complete and filter tasks and launch the timer with client/matter/task context. | 20 | 10 | Not Started | codex/solo-clients-matters | feat(tasks): add solo daily-work flow
F | S2 | codex/solo-work-meter-manual | Work capture | Harden web timer and manual entry with timezone, idle, rounding, recovery and duplicate protection. | Work Meter; current session; session history; manual time form; recovery state | Work-session lifecycle; firm timezone; idempotency; recovery; work-entry projection | Start/pause/resume/stop and manual entry each create one accurate draft work entry with recoverable failure states. | 24 | 12 | Not Started | codex/solo-tasks-daily-work | feat(work): harden timer and manual capture
G | S2 | codex/gmail-research-capture | Work capture | Preserve differentiated Gmail and research capture while simplifying setup for one owner. | Extension setup/status; Gmail review; research review; capture mapping | Extension token; email entries; research capture; mapping and idempotent conversion | Offline captures retry safely; duplicate source references do not duplicate work; mapping updates the unified queue. | 16 | 8 | Not Started | codex/solo-work-meter-manual | feat(capture): adapt Gmail and research for solo use
H | S2 | codex/unified-work-review | Time review | Replace approval queues with one owner-operated work review experience. | Work Entries; entry edit drawer; excluded-work filter; ready-to-bill queue | Status adapter: draft/ready_to_bill/excluded/billed; audit history; batch actions | The owner can correct duration/narrative/matter/rate, exclude work or mark it ready to bill without approval roles. | 12 | 6 | Not Started | codex/gmail-research-capture | feat(work): add unified solo review queue
I | S3 | codex/solo-rates-billables | Billing | Resolve default, client and matter rates and create billables exactly once from reviewed work. | Rate settings; billing workbench; unbilled WIP | Effective rates; rate precedence; amount snapshot; idempotent billable conversion | Correct rate precedence applies; write-up/write-down needs a reason; one work entry produces no more than one billable. | 16 | 8 | Not Started | codex/unified-work-review | feat(billing): simplify rates and billables
J | S3 | codex/expenses-disbursements | Billing | Add reimbursable legal expenses and receipt attachments to matter billing. | Expense list; expense form; receipt preview; matter expenses | Expense model/routes; categories; tax; receipt metadata; billable conversion | An expense can be created, attached to a matter, marked reimbursable and included once in an invoice. | 18 | 9 | Not Started | codex/solo-rates-billables | feat(expenses): add matter disbursements
K | S3 | codex/invoice-core-controls | Invoices | Create a single canonical invoice flow from ready billables with numbering, GST, discounts, locking and revisions. | Invoice list; builder; preview; detail; void/revision dialog | Invoice sequence; server totals; minor-unit money; finalise/lock; revision/void | Invoice totals reconcile; finalised invoices are immutable; work/expenses cannot be invoiced twice. | 22 | 11 | Not Started | codex/expenses-disbursements | feat(invoices): add commercial invoice controls
L | S3 | codex/invoice-pdf-branding | Invoices | Produce one polished professional invoice PDF with solo-practice branding and payment instructions. | Invoice PDF preview; branding settings; print/download states | PDF/HTML generation; logo metadata; bank/UPI instructions | PDF matches invoice totals, includes required identity/tax/payment fields and renders consistently. | 16 | 8 | Not Started | codex/invoice-core-controls | feat(invoices): add branded invoice PDF
M | S4 | codex/invoice-email-delivery | Collections | Send finalised invoices through managed email with delivery history and retry states. | Send invoice dialog; delivery timeline; resend/failure state | Email provider adapter; delivery events; audit trail; retry | A finalised invoice sends to validated recipients and records sent/failed/delivered events without duplicate sends. | 12 | 6 | Not Started | codex/invoice-pdf-branding | feat(invoices): add tracked email delivery
N | S4 | codex/solo-payments-receipts | Payments | Support full/partial payments, reconciliation, receipts, write-offs and accurate outstanding balances. | Payment list/form; invoice payment panel; receipt; write-off dialog; aging view | Payment allocation; invoice status recompute; receipt generation; write-off audit | Partial/full payments update outstanding balances; void invoices reject payments; receipts match cleared payments. | 16 | 8 | Not Started | codex/invoice-email-delivery | feat(payments): complete solo collections flow
O | S4 | codex/solo-dashboard-reports | Insights | Give the lawyer an actionable daily dashboard plus income, WIP, invoice and outstanding reports. | Dashboard; income report; outstanding/aging; time activity; CSV export | Dashboard summary; bounded report queries; CSV exports; data-quality warnings | Dashboard values reconcile with work, invoice and payment sources for the same filters and timezone. | 18 | 9 | Not Started | codex/solo-payments-receipts | feat(reports): add solo income and outstanding insights
P | S4 | codex/solo-release-hardening | Release | Prepare a safe controlled pilot with monitoring, backups, accessibility, mobile polish and end-to-end regression. | Onboarding checklist; support/feedback; production error states; responsive polish | Health/monitoring; backup/restore; rate limits; indexes; audit review; seed/pilot tools | All release gates pass; no P0/P1 defects; backup restore works; 3-5 pilot lawyers can onboard with documented limits. | 26 | 13 | Not Started | codex/solo-dashboard-reports | test(release): harden solo lawyer MVP

## Product Backlog
Prioritised Product Backlog
Editable Scrum backlog; Must items protect security, financial correctness and the end-to-end workflow
Story ID | Sprint | Epic | Story / Task | Branch | Planned h | Priority | Status | Dependency | Acceptance outcome
S1-A1 | S1 | Foundation | Add solo product configuration and route allowlist | codex/solo-product-shell | 4 | Must | Not Started | Previous branch | Only focused MVP routes appear; excluded modules cannot be reached through navigation; loading, empty, error and retry states are reusable.
S1-A2 | S1 | Foundation | Replace sidebar and mobile navigation with focused modules | codex/solo-product-shell | 4 | Should | Not Started | Prior task in branch | Only focused MVP routes appear; excluded modules cannot be reached through navigation; loading, empty, error and retry states are reusable.
S1-A3 | S1 | Foundation | Apply reusable loading/empty/error/offline states | codex/solo-product-shell | 4 | Should | Not Started | Prior task in branch | Only focused MVP routes appear; excluded modules cannot be reached through navigation; loading, empty, error and retry states are reusable.
S1-B1 | S1 | Account | Simplify registration/login and remove role selection | codex/solo-auth-onboarding | 5 | Must | Not Started | Previous branch | A lawyer registers without choosing a role, receives one workspace and can complete/edit practice settings.
S1-B2 | S1 | Account | Create one workspace and owner during registration | codex/solo-auth-onboarding | 5 | Should | Not Started | Prior task in branch | A lawyer registers without choosing a role, receives one workspace and can complete/edit practice settings.
S1-B3 | S1 | Account | Build onboarding for practice, GST, invoice and payment defaults | codex/solo-auth-onboarding | 5 | Should | Not Started | Prior task in branch | A lawyer registers without choosing a role, receives one workspace and can complete/edit practice settings.
S1-B4 | S1 | Account | Complete password reset and session revocation | codex/solo-auth-onboarding | 5 | Should | Not Started | Prior task in branch | A lawyer registers without choosing a role, receives one workspace and can complete/edit practice settings.
S1-C1 | S1 | Security | Add/backfill workspaceId across retained models | codex/workspace-isolation | 5 | Must | Not Started | Previous branch | Workspace A cannot read or mutate Workspace B records; ownership fields cannot be supplied by clients.
S1-C2 | S1 | Security | Resolve authenticated workspace server-side | codex/workspace-isolation | 5 | Should | Not Started | Prior task in branch | Workspace A cannot read or mutate Workspace B records; ownership fields cannot be supplied by clients.
S1-C3 | S1 | Security | Scope all read/write queries and referenced parents | codex/workspace-isolation | 5 | Should | Not Started | Prior task in branch | Workspace A cannot read or mutate Workspace B records; ownership fields cannot be supplied by clients.
S1-C4 | S1 | Security | Add two-workspace isolation suite | codex/workspace-isolation | 5 | Should | Not Started | Prior task in branch | Workspace A cannot read or mutate Workspace B records; ownership fields cannot be supplied by clients.
S1-D1 | S1 | Practice records | Harden client contacts, notes, GST and billing terms | codex/solo-clients-matters | 5 | Must | Not Started | Previous branch | Client and matter CRUD works with validation, archive/reopen, search and workspace ownership.
S1-D2 | S1 | Practice records | Add client archive/search/balance | codex/solo-clients-matters | 5 | Should | Not Started | Prior task in branch | Client and matter CRUD works with validation, archive/reopen, search and workspace ownership.
S1-D3 | S1 | Practice records | Add matter numbering, court fields and billing method | codex/solo-clients-matters | 5 | Should | Not Started | Prior task in branch | Client and matter CRUD works with validation, archive/reopen, search and workspace ownership.
S1-D4 | S1 | Practice records | Reconcile matter financial summary | codex/solo-clients-matters | 5 | Should | Not Started | Prior task in branch | Client and matter CRUD works with validation, archive/reopen, search and workspace ownership.
S2-E1 | S2 | Daily work | Simplify task CRUD for one owner | codex/solo-tasks-daily-work | 6.7 | Must | Not Started | Previous branch | The owner can create, complete and filter tasks and launch the timer with client/matter/task context.
S2-E2 | S2 | Daily work | Add checklist, priority, due and overdue filters | codex/solo-tasks-daily-work | 6.7 | Should | Not Started | Prior task in branch | The owner can create, complete and filter tasks and launch the timer with client/matter/task context.
S2-E3 | S2 | Daily work | Launch pre-filled meter context from task | codex/solo-tasks-daily-work | 6.7 | Should | Not Started | Prior task in branch | The owner can create, complete and filter tasks and launch the timer with client/matter/task context.
S2-F1 | S2 | Work capture | Harden start/pause/resume/stop lifecycle | codex/solo-work-meter-manual | 6 | Must | Not Started | Previous branch | Start/pause/resume/stop and manual entry each create one accurate draft work entry with recoverable failure states.
S2-F2 | S2 | Work capture | Add timezone, idle and rounding rules | codex/solo-work-meter-manual | 6 | Should | Not Started | Prior task in branch | Start/pause/resume/stop and manual entry each create one accurate draft work entry with recoverable failure states.
S2-F3 | S2 | Work capture | Add manual entry and edit validation | codex/solo-work-meter-manual | 6 | Should | Not Started | Prior task in branch | Start/pause/resume/stop and manual entry each create one accurate draft work entry with recoverable failure states.
S2-F4 | S2 | Work capture | Add idempotency and crash recovery | codex/solo-work-meter-manual | 6 | Should | Not Started | Prior task in branch | Start/pause/resume/stop and manual entry each create one accurate draft work entry with recoverable failure states.
S2-G1 | S2 | Work capture | Simplify extension authentication/setup | codex/gmail-research-capture | 5.3 | Must | Not Started | Previous branch | Offline captures retry safely; duplicate source references do not duplicate work; mapping updates the unified queue.
S2-G2 | S2 | Work capture | Harden Gmail/research mapping | codex/gmail-research-capture | 5.3 | Should | Not Started | Prior task in branch | Offline captures retry safely; duplicate source references do not duplicate work; mapping updates the unified queue.
S2-G3 | S2 | Work capture | Verify offline retry and duplicate sourceRef protection | codex/gmail-research-capture | 5.3 | Should | Not Started | Prior task in branch | Offline captures retry safely; duplicate source references do not duplicate work; mapping updates the unified queue.
S2-H1 | S2 | Time review | Create unified Work Entries list | codex/unified-work-review | 4 | Must | Not Started | Previous branch | The owner can correct duration/narrative/matter/rate, exclude work or mark it ready to bill without approval roles.
S2-H2 | S2 | Time review | Map legacy states to draft/ready/excluded/billed | codex/unified-work-review | 4 | Should | Not Started | Prior task in branch | The owner can correct duration/narrative/matter/rate, exclude work or mark it ready to bill without approval roles.
S2-H3 | S2 | Time review | Add edit, batch mark-ready and exclude actions | codex/unified-work-review | 4 | Should | Not Started | Prior task in branch | The owner can correct duration/narrative/matter/rate, exclude work or mark it ready to bill without approval roles.
S3-I1 | S3 | Billing | Implement rate precedence and effective dates | codex/solo-rates-billables | 5.3 | Must | Not Started | Previous branch | Correct rate precedence applies; write-up/write-down needs a reason; one work entry produces no more than one billable.
S3-I2 | S3 | Billing | Snapshot rate and amount on work | codex/solo-rates-billables | 5.3 | Should | Not Started | Prior task in branch | Correct rate precedence applies; write-up/write-down needs a reason; one work entry produces no more than one billable.
S3-I3 | S3 | Billing | Create idempotent billable conversion and WIP | codex/solo-rates-billables | 5.3 | Should | Not Started | Prior task in branch | Correct rate precedence applies; write-up/write-down needs a reason; one work entry produces no more than one billable.
S3-J1 | S3 | Billing | Create expense model, API and screens | codex/expenses-disbursements | 6 | Must | Not Started | Previous branch | An expense can be created, attached to a matter, marked reimbursable and included once in an invoice.
S3-J2 | S3 | Billing | Add receipt upload authorization | codex/expenses-disbursements | 6 | Should | Not Started | Prior task in branch | An expense can be created, attached to a matter, marked reimbursable and included once in an invoice.
S3-J3 | S3 | Billing | Convert reimbursable expense once into billing | codex/expenses-disbursements | 6 | Should | Not Started | Prior task in branch | An expense can be created, attached to a matter, marked reimbursable and included once in an invoice.
S3-K1 | S3 | Invoices | Create canonical billables-to-invoice route | codex/invoice-core-controls | 5.5 | Must | Not Started | Previous branch | Invoice totals reconcile; finalised invoices are immutable; work/expenses cannot be invoiced twice.
S3-K2 | S3 | Invoices | Add sequence, GST, discounts and minor-unit totals | codex/invoice-core-controls | 5.5 | Should | Not Started | Prior task in branch | Invoice totals reconcile; finalised invoices are immutable; work/expenses cannot be invoiced twice.
S3-K3 | S3 | Invoices | Lock finalised invoices and add void/revision | codex/invoice-core-controls | 5.5 | Should | Not Started | Prior task in branch | Invoice totals reconcile; finalised invoices are immutable; work/expenses cannot be invoiced twice.
S3-K4 | S3 | Invoices | Add duplicate/concurrency protection | codex/invoice-core-controls | 5.5 | Should | Not Started | Prior task in branch | Invoice totals reconcile; finalised invoices are immutable; work/expenses cannot be invoiced twice.
S3-L1 | S3 | Invoices | Add practice branding and payment instructions | codex/invoice-pdf-branding | 5.3 | Must | Not Started | Previous branch | PDF matches invoice totals, includes required identity/tax/payment fields and renders consistently.
S3-L2 | S3 | Invoices | Build verified invoice HTML/PDF | codex/invoice-pdf-branding | 5.3 | Should | Not Started | Prior task in branch | PDF matches invoice totals, includes required identity/tax/payment fields and renders consistently.
S3-L3 | S3 | Invoices | Test long content, GST and authorization | codex/invoice-pdf-branding | 5.3 | Should | Not Started | Prior task in branch | PDF matches invoice totals, includes required identity/tax/payment fields and renders consistently.
S4-M1 | S4 | Collections | Integrate managed email provider | codex/invoice-email-delivery | 4 | Must | Not Started | Previous branch | A finalised invoice sends to validated recipients and records sent/failed/delivered events without duplicate sends.
S4-M2 | S4 | Collections | Add delivery audit timeline and retries | codex/invoice-email-delivery | 4 | Should | Not Started | Prior task in branch | A finalised invoice sends to validated recipients and records sent/failed/delivered events without duplicate sends.
S4-M3 | S4 | Collections | Prevent duplicate invoice sends | codex/invoice-email-delivery | 4 | Should | Not Started | Prior task in branch | A finalised invoice sends to validated recipients and records sent/failed/delivered events without duplicate sends.
S4-N1 | S4 | Payments | Complete partial/full payment allocation | codex/solo-payments-receipts | 5.3 | Must | Not Started | Previous branch | Partial/full payments update outstanding balances; void invoices reject payments; receipts match cleared payments.
S4-N2 | S4 | Payments | Add receipts and write-off audit | codex/solo-payments-receipts | 5.3 | Should | Not Started | Prior task in branch | Partial/full payments update outstanding balances; void invoices reject payments; receipts match cleared payments.
S4-N3 | S4 | Payments | Reconcile invoice status and aging | codex/solo-payments-receipts | 5.3 | Should | Not Started | Prior task in branch | Partial/full payments update outstanding balances; void invoices reject payments; receipts match cleared payments.
S4-O1 | S4 | Insights | Build daily solo dashboard | codex/solo-dashboard-reports | 4.5 | Must | Not Started | Previous branch | Dashboard values reconcile with work, invoice and payment sources for the same filters and timezone.
S4-O2 | S4 | Insights | Add income, WIP, aging and activity reports | codex/solo-dashboard-reports | 4.5 | Should | Not Started | Prior task in branch | Dashboard values reconcile with work, invoice and payment sources for the same filters and timezone.
S4-O3 | S4 | Insights | Add bounded filters and CSV exports | codex/solo-dashboard-reports | 4.5 | Should | Not Started | Prior task in branch | Dashboard values reconcile with work, invoice and payment sources for the same filters and timezone.
S4-O4 | S4 | Insights | Reconcile report totals to source data | codex/solo-dashboard-reports | 4.5 | Should | Not Started | Prior task in branch | Dashboard values reconcile with work, invoice and payment sources for the same filters and timezone.
S4-P1 | S4 | Release | Add monitoring, health, limits and indexes | codex/solo-release-hardening | 6.5 | Must | Not Started | Previous branch | All release gates pass; no P0/P1 defects; backup restore works; 3-5 pilot lawyers can onboard with documented limits.
S4-P2 | S4 | Release | Run backup/restore and security regression | codex/solo-release-hardening | 6.5 | Should | Not Started | Prior task in branch | All release gates pass; no P0/P1 defects; backup restore works; 3-5 pilot lawyers can onboard with documented limits.
S4-P3 | S4 | Release | Complete accessibility/mobile polish | codex/solo-release-hardening | 6.5 | Should | Not Started | Prior task in branch | All release gates pass; no P0/P1 defects; backup restore works; 3-5 pilot lawyers can onboard with documented limits.
S4-P4 | S4 | Release | Prepare seed data, guide and pilot onboarding | codex/solo-release-hardening | 6.5 | Should | Not Started | Prior task in branch | All release gates pass; no P0/P1 defects; backup restore works; 3-5 pilot lawyers can onboard with documented limits.

## Screen Inventory
Solo-Lawyer Screen Inventory
Retained, revised and new screens only; enterprise-only modules stay hidden from the MVP
Module | Screen | Route | Action | Sprint | Branch
Account | Login | /login | Keep / simplify | S1 | B
Account | Register | /register | Revise | S1 | B
Account | Password recovery | /forgot-password | Complete | S1 | B
Account | Solo onboarding | /onboarding | New | S1 | B
Account | Owner profile/settings | /app/settings | Revise | S1 | B
Dashboard | Solo dashboard | /app/dashboard | Revise | S4 | O
Clients | Client list | /app/clients | Keep / harden | S1 | D
Clients | Client form | /app/clients/new | Keep / harden | S1 | D
Clients | Client detail & balance | /app/clients/:id | Revise | S1 | D
Matters | Matter list | /app/matters | Keep / harden | S1 | D
Matters | Matter form | /app/matters/new | Revise | S1 | D
Matters | Matter workspace | /app/matters/:id | Revise | S1 | D
Tasks | Task list / today | /app/tasks | Simplify | S2 | E
Tasks | Task form/detail | /app/tasks/:id | Keep / harden | S2 | E
Work | Work Meter | /app/work-meter | Keep / harden | S2 | F
Work | Manual time entry | /app/work-entries/new | Revise | S2 | F
Work | Unified Work Entries | /app/work-entries | New/compose | S2 | H
Work | Entry edit/review | /app/work-entries/:id | New/compose | S2 | H
Capture | Extension setup/status | /app/capture/setup | Simplify | S2 | G
Capture | Gmail/research review | /app/captured-work | Compose | S2 | G
Billing | Rates settings | /app/settings/rates | Revise | S3 | I
Billing | Billing workbench / WIP | /app/billing | Revise | S3 | I
Expenses | Expense list | /app/expenses | New | S3 | J
Expenses | Expense form | /app/expenses/new | New | S3 | J
Invoices | Invoice list | /app/invoices | Keep / harden | S3 | K
Invoices | Invoice builder | /app/invoices/new | Revise | S3 | K
Invoices | Invoice detail | /app/invoices/:id | Keep / harden | S3 | K
Invoices | PDF preview | /app/invoices/:id/preview | Complete | S3 | L
Invoices | Send/delivery history | /app/invoices/:id/send | Complete | S4 | M
Payments | Payments and allocation | /app/payments | Keep / harden | S4 | N
Payments | Receipt | /app/payments/:id/receipt | New | S4 | N
Reports | Income and outstanding | /app/reports | Revise | S4 | O

## API Mapping
Backend / API Mapping
Branch-level contracts to confirm before implementation; update exact endpoints as routes are finalised
Branch | Sprint | Domain | Current backend direction | Required change | Isolation requirement | Contract status
codex/solo-product-shell | S1 | Foundation | PRODUCT_MODE configuration; route exposure map; no schema change | Introduce solo product mode, focused navigation and shared UX states while hiding enterprise-only modules. | Every read/write scoped to authenticated workspace | To Verify
codex/solo-auth-onboarding | S1 | Account | Auth current-user routes; workspace creation; owner profile/settings; session revocation | Simplify registration and login to one owner account and capture practice, tax, invoice and payment defaults during onboarding. | Every read/write scoped to authenticated workspace | To Verify
codex/workspace-isolation | S1 | Security | workspaceId/firmId migration; request workspace context; scoped queries; ownership validators | Enforce workspace ownership across every retained resource and migrate legacy firm records safely. | Every read/write scoped to authenticated workspace | To Verify
codex/solo-clients-matters | S1 | Practice records | Client contacts/notes; matter numbering; matter billing method; scoped summaries | Complete client and matter records for a solo practice, including contacts, GST, billing terms, court details and financial summaries. | Every read/write scoped to authenticated workspace | To Verify
codex/solo-tasks-daily-work | S2 | Daily work | Task CRUD; due/priority/checklist; meter context handoff | Simplify tasks for one lawyer and allow any task to launch a pre-filled work session. | Every read/write scoped to authenticated workspace | To Verify
codex/solo-work-meter-manual | S2 | Work capture | Work-session lifecycle; firm timezone; idempotency; recovery; work-entry projection | Harden web timer and manual entry with timezone, idle, rounding, recovery and duplicate protection. | Every read/write scoped to authenticated workspace | To Verify
codex/gmail-research-capture | S2 | Work capture | Extension token; email entries; research capture; mapping and idempotent conversion | Preserve differentiated Gmail and research capture while simplifying setup for one owner. | Every read/write scoped to authenticated workspace | To Verify
codex/unified-work-review | S2 | Time review | Status adapter: draft/ready_to_bill/excluded/billed; audit history; batch actions | Replace approval queues with one owner-operated work review experience. | Every read/write scoped to authenticated workspace | To Verify
codex/solo-rates-billables | S3 | Billing | Effective rates; rate precedence; amount snapshot; idempotent billable conversion | Resolve default, client and matter rates and create billables exactly once from reviewed work. | Every read/write scoped to authenticated workspace | To Verify
codex/expenses-disbursements | S3 | Billing | Expense model/routes; categories; tax; receipt metadata; billable conversion | Add reimbursable legal expenses and receipt attachments to matter billing. | Every read/write scoped to authenticated workspace | To Verify
codex/invoice-core-controls | S3 | Invoices | Invoice sequence; server totals; minor-unit money; finalise/lock; revision/void | Create a single canonical invoice flow from ready billables with numbering, GST, discounts, locking and revisions. | Every read/write scoped to authenticated workspace | To Verify
codex/invoice-pdf-branding | S3 | Invoices | PDF/HTML generation; logo metadata; bank/UPI instructions | Produce one polished professional invoice PDF with solo-practice branding and payment instructions. | Every read/write scoped to authenticated workspace | To Verify
codex/invoice-email-delivery | S4 | Collections | Email provider adapter; delivery events; audit trail; retry | Send finalised invoices through managed email with delivery history and retry states. | Every read/write scoped to authenticated workspace | To Verify
codex/solo-payments-receipts | S4 | Payments | Payment allocation; invoice status recompute; receipt generation; write-off audit | Support full/partial payments, reconciliation, receipts, write-offs and accurate outstanding balances. | Every read/write scoped to authenticated workspace | To Verify
codex/solo-dashboard-reports | S4 | Insights | Dashboard summary; bounded report queries; CSV exports; data-quality warnings | Give the lawyer an actionable daily dashboard plus income, WIP, invoice and outstanding reports. | Every read/write scoped to authenticated workspace | To Verify
codex/solo-release-hardening | S4 | Release | Health/monitoring; backup/restore; rate limits; indexes; audit review; seed/pilot tools | Prepare a safe controlled pilot with monitoring, backups, accessibility, mobile polish and end-to-end regression. | Every read/write scoped to authenticated workspace | To Verify

## Risks and Gates
Risks, Release Gates and Non-Goals
Use this sheet in sprint reviews; no release while a critical gate is open
Risk ID | Severity | Risk | Impact | Mitigation | Due
R1 | Critical | Cross-workspace data access | Security incident and pilot failure | Mandatory workspace scoping, two-workspace tests, no caller-supplied ownership | S1
R2 | Critical | Duplicate work-to-billable or billable-to-invoice conversion | Overbilling and loss of trust | Unique indexes, idempotency keys, transactional conversion and concurrency tests | S3
R3 | High | Financial rounding/GST mismatch | Invoice disputes | Integer minor units, server-side totals and golden fixtures | S3
R4 | High | Gmail DOM or extension instability | Lost work capture | Retry queue, visible health state and manual-entry fallback | S2
R5 | High | Solo developer scope expansion | Missed eight-week release | Frozen non-goals, 8-hour sprint buffer and change-control rule | All
R6 | Medium | Email/PDF provider failure | Invoice cannot be delivered | Managed provider sandbox, retry and download fallback | S4
R7 | Medium | Insufficient pilot feedback | Wrong workflow optimisations | Weekly pilot interviews, event metrics and in-product feedback | S4
Gate ID | Release gate |  |  |  | Status
G1 | Workspace A cannot read or mutate Workspace B data. |  |  |  | Open
G2 | Every supported capture produces at most one work entry. |  |  |  | Open
G3 | Every work entry and expense can be invoiced at most once. |  |  |  | Open
G4 | Invoice totals, payment allocations and reports reconcile exactly. |  |  |  | Open
G5 | Finalised invoices are locked and corrections are audited. |  |  |  | Open
G6 | Backup restoration, error monitoring and production health checks pass. |  |  |  | Open
G7 | All retained screens have loading, empty, error and recovery states. |  |  |  | Open
G8 | No P0/P1 defect remains open at pilot launch. |  |  |  | Open
Non-goal | Decision
NG1 | Multi-user firm administration
NG2 | RBAC and team permissions
NG3 | Partner or billing-manager approvals
NG4 | Attendance, HR and payroll
NG5 | Workforce monitoring and analytics
NG6 | Trust accounting and general ledger
NG7 | WhatsApp/SMS and meeting recording
NG8 | Automatic court feed or legal research AI
NG9 | Native mobile applications
NG10 | Deep CRM/ERP integrations during MVP

## Daily Scrum Log
Daily Scrum Log
Forty working-day execution log; one primary outcome per day
Day | Sprint | Date | Primary outcome | Branch | Planned h | Actual h | Status | Blocker / Decision | Verification evidence
1 | S1 |  |  | codex/solo-product-shell | 8 |  | Not Started
2 | S1 |  |  | codex/solo-product-shell | 8 |  | Not Started
3 | S1 |  |  | codex/solo-product-shell | 8 |  | Not Started
4 | S1 |  |  | codex/solo-auth-onboarding | 8 |  | Not Started
5 | S1 |  |  | codex/solo-auth-onboarding | 8 |  | Not Started
6 | S1 |  |  | codex/workspace-isolation | 8 |  | Not Started
7 | S1 |  |  | codex/workspace-isolation | 8 |  | Not Started
8 | S1 |  |  | codex/workspace-isolation | 8 |  | Not Started
9 | S1 |  |  | codex/solo-clients-matters | 8 |  | Not Started
10 | S1 |  |  | codex/solo-clients-matters | 8 |  | Not Started
11 | S2 |  |  | codex/solo-tasks-daily-work | 8 |  | Not Started
12 | S2 |  |  | codex/solo-tasks-daily-work | 8 |  | Not Started
13 | S2 |  |  | codex/solo-tasks-daily-work | 8 |  | Not Started
14 | S2 |  |  | codex/solo-work-meter-manual | 8 |  | Not Started
15 | S2 |  |  | codex/solo-work-meter-manual | 8 |  | Not Started
16 | S2 |  |  | codex/gmail-research-capture | 8 |  | Not Started
17 | S2 |  |  | codex/gmail-research-capture | 8 |  | Not Started
18 | S2 |  |  | codex/gmail-research-capture | 8 |  | Not Started
19 | S2 |  |  | codex/unified-work-review | 8 |  | Not Started
20 | S2 |  |  | codex/unified-work-review | 8 |  | Not Started
21 | S3 |  |  | codex/solo-rates-billables | 8 |  | Not Started
22 | S3 |  |  | codex/solo-rates-billables | 8 |  | Not Started
23 | S3 |  |  | codex/solo-rates-billables | 8 |  | Not Started
24 | S3 |  |  | codex/expenses-disbursements | 8 |  | Not Started
25 | S3 |  |  | codex/expenses-disbursements | 8 |  | Not Started
26 | S3 |  |  | codex/invoice-core-controls | 8 |  | Not Started
27 | S3 |  |  | codex/invoice-core-controls | 8 |  | Not Started
28 | S3 |  |  | codex/invoice-core-controls | 8 |  | Not Started
29 | S3 |  |  | codex/invoice-pdf-branding | 8 |  | Not Started
30 | S3 |  |  | codex/invoice-pdf-branding | 8 |  | Not Started
31 | S4 |  |  | codex/invoice-email-delivery | 8 |  | Not Started
32 | S4 |  |  | codex/invoice-email-delivery | 8 |  | Not Started
33 | S4 |  |  | codex/invoice-email-delivery | 8 |  | Not Started
34 | S4 |  |  | codex/solo-payments-receipts | 8 |  | Not Started
35 | S4 |  |  | codex/solo-payments-receipts | 8 |  | Not Started
36 | S4 |  |  | codex/solo-dashboard-reports | 8 |  | Not Started
37 | S4 |  |  | codex/solo-dashboard-reports | 8 |  | Not Started
38 | S4 |  |  | codex/solo-dashboard-reports | 8 |  | Not Started
39 | S4 |  |  | codex/solo-release-hardening | 8 |  | Not Started
40 | S4 |  |  | codex/solo-release-hardening | 8 |  | Not Started