## Summary
BillSync Frontend Branch Tracker
All screens + API wiring branch plan generated from BillSync_Frontend_AI_Prompts_All_Screens_API_Branches.docx
Metric | Value
Total branches | 32
Product scope | 75+ product screens
Fallback scope | 24 states
Design folder | E:/Shwetal/UI Design/stitch_billsync_legal_platform_ui
Backend folder | E:/Shwetal/legal-billing-backend

## Branch Tracker
No. | Branch | Codex Prompt Goal | Images Created / Screens Designed | Acceptance Criteria | Commit Message
A | feat/frontend-bootstrap | Create the new React + Tailwind frontend foundation with full route map, public/protected layouts, sidebar/topbar shell, and placeholders for all product and fallback screens. | Global app shell, navigation, route placeholders, layout frames | App runs; every planned route renders a placeholder; sidebar and mobile nav work; routes are grouped by role and module. | chore(frontend): bootstrap BillSync React Tailwind shell
B | feat/design-system | Build the reusable BillSync design system components before feature screens: controls, tables, tabs, modals, state components, and progress indicators. | Component gallery, buttons, forms, status badges, tables, fallback cards | Component gallery renders all primitives; states support loading/disabled/focus; palette is centralized. | feat(ui): add BillSync design system
C | feat/api-client-contracts | Create frontend API service modules, request helpers, auth headers, pagination helpers, upload helpers, and normalized error handling for all backend areas. | No UI image; backend/API service layer and API mapping sheet support | API modules exist for available backend resources; normalized errors never leak raw technical text into UI. | feat(api): add frontend API client and service contracts
D | feat/auth-users-permissions | Implement auth, user access, protected routes, profile, user management, roles, and permissions using backend auth/user APIs. | Login, register/invite, forgot/reset, profile, user management, permissions | Login/logout works; current user loads; user list/profile screens connect; role gates work. | feat(auth): implement user access flows
E | feat/fallback-state-system | Implement all reusable fallback, loading, empty, error, permission, retry, and unavailable states for the whole product. | 24 fallback states, fallback gallery, loading skeletons, empty states, error states | Fallback gallery includes all 24 states with plain-language copy and retry/reconnect actions. | feat(ui): implement fallback state system
F | feat/global-dashboard-common | Build role dashboards, lawyer dashboard, notifications, global search, help guide, and My Setup Status confidence layer. | Role dashboards, Lawyer Dashboard, Admin Dashboard, Notification Center, Search, Help, My Setup Status | Dashboards render with real/adapted data; setup cards show working/needs-attention states. | feat(dashboard): add global dashboards and setup status
G | feat/clients-api | Connect client management screens to client, invoice, and payment summary backend data. | Client List, Client Create/Edit, Client Detail, Client Contacts, Client Billing Summary | Client CRUD works; contacts and billing summary render; empty/error states exist. | feat(clients): connect client management screens
H | feat/matters-core-api | Implement core Matter screens using backend case and case-assignment APIs while keeping lawyer-facing terminology as Matter. | Matter List, Matter Create/Edit, Matter Detail Overview, Matter Team & Assignments | Matter list/detail and assignments render; create/edit validates; empty states exist. | feat(matters): connect matter core screens
I | feat/matter-timeline-docs-billing-audit | Implement the advanced Matter Detail tabs and connect timeline, documents, billing, payments, and audit/integration data where available. | Matter Timeline, Matter Documents, Matter Billing, Matter Audit | Matter tabs render real/adapted data and honest missing-provider states. | feat(matters): add timeline documents billing audit tabs
J | feat/tasks-daily-work | Build task and daily work workflows, using adapters if task APIs are missing, and connect task context into the Work Meter. | My Tasks, Task Board, Task Detail, Task Create/Edit, My Work Today | Task pages render; task detail can launch meter context; missing task backend is documented. | feat(tasks): implement daily task workflows
K | feat/calendar-hearings | Build calendar and court hearing manual time workflows, using activity/time-entry APIs and honest calendar-provider fallback states. | Calendar, Hearing Dashboard, Court Hearing Time Entry, Calendar Not Connected | Calendar/hearing pages render; hearing time saves where backend allows; calendar fallback exists. | feat(calendar): add hearing and calendar workflows
L | feat/work-meter-time-capture | Implement the Work Meter and time-capture lifecycle from session start/stop to manual time and submit-for-approval. | Work Meter, Work Session History, Manual Time Entry, Captured Work Review, Submit Work for Approval | Start/stop/save works; save-failed state preserves time; submit-for-approval flow exists. | feat(work): connect meter and time capture
M | feat/chrome-extension-setup-status | Build guided Chrome extension setup, extension status checks, and troubleshooting screens using extension docs and email-entry backend behavior. | Chrome Extension Setup, Chrome Extension Status, Extension Troubleshooting | Setup guide and status cards render; test actions are available; extension not connected states exist. | feat(extension): add setup status troubleshooting
N | feat/email-research-capture | Connect Gmail and research capture review screens to email-entry APIs, mapping, conversion, and billable/time workflows where available. | Gmail Capture Review, Research Capture Review, Capture Mapping, Conversion States | Captured lists render; map to client/matter works; converted/failed/empty states exist. | feat(capture): connect Gmail and research review
O | feat/call-meeting-recorder | Create call/meeting recorder screens with honest unavailable/not-configured states if recorder APIs are missing. | Call/Meeting Recorder, Recording Library, Recording Detail with transcript and matter link | Recorder pages render; permission blocked/unavailable states exist; no fake recording persistence. | feat(recorder): add call meeting recorder screens
P | feat/billables-rates-api | Connect billables, approval queue, billable detail, and rate-card workflows to backend billable and rate APIs. | Billables List, Billable Detail, Billable Approval Queue, Rate Cards | Billable filters, approval queue, detail, and rate cards work with success/failure states. | feat(billing): connect billables and rates
Q | feat/invoices-api | Build invoice list, builder, detail, send/share, and templates using invoice generation and status APIs. | Invoice List, Invoice Builder, Invoice Detail, Invoice Send/Share, Invoice Templates | Invoice list/detail/builder render; generation failure state exists; no fake real email/PDF claim. | feat(invoices): connect invoice workflows
R | feat/payments-portal-reconciliation | Implement payment dashboard, payment entry, client payment portal state, and reconciliation using payment APIs and honest gateway fallback. | Payment Dashboard, Payment Entry, Client Payment Portal, Payment Reconciliation, Payment Failed | Payment record/reconcile works where backend allows; portal state is honest; failure states exist. | feat(payments): add payment portal and reconciliation
S | feat/finance-reports-audit | Connect finance dashboard, reports, audit logs, AR/WIP/revenue/utilization views using analytics, KPI, report, payment, invoice, and integration-log data. | Finance Dashboard, Reports, Audit Logs, AR/WIP/Revenue/Utilization Views | Finance KPIs render; report exports trigger where available; audit logs show available events. | feat(finance): connect reports and audit screens
T | feat/gst-tds-tax | Build GST/TDS dashboards and settings using firm tax settings and invoice tax fields where available, with honest TDS not-configured state if missing. | GST Dashboard, GST Settings, TDS Dashboard, TDS Settings, Tax Summary States | GST settings render; TDS not-configured state exists if no API; tax pages avoid fake compliance. | feat(tax): add GST and TDS screens
U | feat/hr-people | Build HR dashboard, people directory, employee profiles, and workload/attendance overview using user/profile/time data where available. | HR Dashboard, Team Directory, Employee Profile, Attendance/Workload Overview | People screens render real users; workload/adapters are clear; empty states exist. | feat(hr): add people and workload screens
V | feat/payroll | Create payroll runs, payroll detail, compensation placeholders, and payroll not-configured state without pretending backend payroll exists. | Payroll Runs, Payroll Detail, Compensation Placeholder, Payroll Not Configured | Payroll screens render without pretending backend exists; admin sees required setup steps. | feat(payroll): add payroll workflow shell
W | feat/storage-documents | Implement storage library, upload, document viewer, storage settings, and matter document links using Zoho WorkDrive/attachments and provider adapters. | Storage Library, Upload File, Document Viewer, Storage Settings, Matter Document Links | Document library/viewer/upload states render; provider-not-connected and upload-failed states exist. | feat(storage): connect document storage screens
X | feat/ai-assistant-core | Connect core AI assistant modes for email writing and research/text assistance to available AI endpoints. | AI Assistant, AI Email Writer, AI Research Assistant | AI modes call backend where available; delayed/unavailable states exist; outputs are clearly editable. | feat(ai): connect AI assistant core
Y | feat/ai-documents-rag | Create AI document summary, document creation, and RAG chatbot shells, wiring available APIs and clearly marking indexing/RAG gaps. | Document Summary, Document Creation, RAG Chatbot, Matter Document Q&A Shell | Doc summary/create shells render; RAG does not fake document-grounded answers without backend support. | feat(ai): add document summary creation and RAG screens
Z | feat/communications-whatsapp-sms | Build WhatsApp and SMS communication screens with provider setup, templates, logs, and not-connected states if APIs are missing. | WhatsApp Inbox, WhatsApp Templates, SMS Center, SMS Templates, Communication Logs | Communication screens render; no fake send confirmation; provider status is clear. | feat(comms): add WhatsApp SMS communication screens
AA | feat/court-daily-sync | Create court daily sync dashboard, court case match, verdict detail, and court sync settings with not-connected/sync-failed states if feed APIs are missing. | Court Daily Sync Dashboard, Court Case Match, Court Verdict Detail, Court Sync Settings | Court screens render; manual hearing and live court sync are visually distinct. | feat(court): add court daily sync screens
AB | feat/zoho-integration-api | Connect Zoho integration screens to backend Zoho auth, status, sync, WorkDrive, attachment, and log routes. | Zoho Connect/Status/Sync, WorkDrive Link, Zoho Sync Logs | Zoho connect/status works; sync actions and logs render; provider errors are friendly. | feat(integrations): connect Zoho workflows
AC | feat/aws-google-integrations | Add AWS/Google provider setup and cloud storage integration states, using adapters and clear setup requirements if APIs are missing. | AWS Integration Setup, Google Integration Setup, Cloud Provider Status, Integration Not Connected | AWS/Google screens render; not-connected and setup states are clear. | feat(integrations): add AWS and Google provider screens
AD | feat/settings-admin-controls | Implement settings, firm setup, permissions refinements, and defaults for invoice, tax, storage, notifications, and admin controls. | Settings, Firm Setup, Permissions Matrix, Invoice/Tax/Storage/Notification Defaults | Settings screens render; admin-only gating works; validation/fallback states exist. | feat(settings): add admin settings and controls
AE | style/responsive-accessibility-copy-polish | Audit and polish all routes for responsive layout, accessibility, keyboard focus, contrast, reduced motion, text overflow, and non-technical copy. | All implemented screens and fallback states polished across desktop/tablet/mobile | No horizontal overflow at 360px; focus states visible; reduced-motion respected; copy is non-technical. | style(ui): polish responsiveness accessibility and copy
AF | test/e2e-demo-hardening | Run full product demo QA across lawyer, admin, finance, integration, and fallback flows; add smoke tests and final backend-gap report. | All product screens, all fallback states, demo path, QA report | Build passes; demo path works; backend gaps are documented; all major fallbacks are reachable. | test(frontend): harden full product demo flows